JK LIFESTYLE DIGITAL ECOSYSTEM

# Technical Architecture, Execution Roadmap & Costing Plan

Website  |  Super App  |  Enterprise Platform (ERP)  |  Clinical  |  Data, Events & AI

| Prepared for | JK Lifestyle Ltd. (Group Management Office) |
| --- | --- |
| Prepared as | CTO / Technical Architect board proposal and execution baseline |
| Baseline | JK Lifestyle Technical Development Plan, September 2026 |
| Planning horizon | 24 months |
| Budget currency | BDT (Bangladeshi Taka) |

Budget status: planning baseline, not a vendor quotation. Approval should follow HR salary validation, cloud sizing, license choice and supplier quotations.

# 1. Executive Summary

Architectural baseline. The program is designed as one shared digital ecosystem rather than separate applications. A shared JK ID, API Gateway and cross-cutting control plane sit above two deliberately separated enterprise cores: Odoo Community as the commercial/financial system of record, and a custom JK ERP/Clinical platform for differentiated clinical, workforce and operational workflows. Odoo Community processes Product, Inventory/Warehouse, Procurement, POS, outlet sales, online/e-commerce sales, customer invoicing and Accounting. The custom ERP/Clinical platform owns Doctor Profile, Patient/Appointment workflow, OPD/EMR, Care Plan, Clinical Billing workflow, ARM, Attendance and Payroll calculation. Financial outcomes from custom workflows are posted to Odoo through controlled APIs/events so there is only one financial ledger. The architecture remains modular/bounded-domain, event-enabled where useful, and preserves clean seams for later service extraction.

| Metric | Base Planning Value | Comment |
| --- | --- | --- |
| Program duration | 24 months | Overlapping phase delivery; two-week sprint cadence |
| Build-team peak | ~14 active technical FTE at peak | Ramp up by phase; no separate PO, Data/AI, ML or moderator headcount |
| 24-month development & specialist cost | BDT 26.9M | Loaded in-house cost plus outsourced Odoo/UIUX support; consolidated roles absorbed by Tech Lead |
| Cloud / platform run cost | BDT 10.0M | Gradually increases with App, media and AI usage |
| Other delivery costs | BDT 11.5M | AI/API, SaaS, security, equipment, migration/training, recruitment |
| Base spend before contingency | BDT 48.4M | Cash plan for approved work |
| Contingency reserve | BDT 5.8M (12%) | Held centrally; released only through change/risk control |
| Total planning envelope | BDT 54.3M (~5.43 crore) | Recommended approval ceiling for the 24-month baseline |

Important exclusions. Payment/MFS transaction charges are treated as business transaction costs tied to GMV and are not included in the project envelope. The ERP baseline now assumes Odoo Community (open-source), so no Odoo Enterprise license fee is included. Any paid hosting, third-party Odoo add-ons, implementation/support subscription, taxes/VAT, or unusually high video/AI consumption should be budgeted separately if applicable.

# 2. Planning Assumptions & Guardrails

•  Target design scale: 11 outlets initially, 500-700 daily patients, 5,000 peak concurrent users and 50,000+ registered online customers in Year 1. Infrastructure is sized progressively, not pre-purchased for full scale.

•  JK Tech is treated as having no pre-existing engineering bench at project start; recruitment is therefore on the critical path.

•  Odoo Community is the commercial/financial source of truth for Product, Inventory/Warehouse, Procurement, POS, outlet and online/e-commerce sales, customer invoices and Accounting. Custom JK ERP/Clinical owns Doctor, Appointment, OPD/EMR, Care Plan, Clinical Billing, ARM, Attendance and Payroll workflows; integration is API/event based.

•  No big-bang migration. Odoo/Excel/POS/website/clinical migrations use staging rehearsal, parallel run, reconciliation and outlet/module-by-module cut-over.

•  Two-week sprints are mandatory. Every sprint ends with a demo and targeted UAT; each major go-live requires regression, performance, security and business acceptance gates.

•  Identity, custom ERP/Clinical and DevOps remain in-house. Odoo specialist work may be outsourced with knowledge transfer; Product Owner, Data/AI, ML/AI and Community Moderation remain consolidated under the Tech Lead / Architect in this budget.

•  Cloud and third-party budgets are reviewed monthly with alerts at 70%, 85% and 100% of the approved envelope.

# 3. System Architecture & Technical Design

Architecture objective. Build one coherent digital operating platform with explicit ownership boundaries, a shared identity/control plane, API-first integration and event capture from day one. The design prioritizes business continuity, maintainability, health-data protection and future service extraction without paying day-one microservice operational cost.

## 3.1 Architecture decisions & guardrails

| Decision | Choice | Technical rationale |
| --- | --- | --- |
| Architecture style | Modular monolith / bounded domains | 5-6 domain-aligned modules/services; extract only when scaling, compliance or workload isolation requires it. |
| ERP strategy | Hybrid: Odoo Community + Custom ERP/Clinical | Odoo Community owns commercial/financial processing (Product, Inventory/Warehouse, Procurement, POS, outlet and online/e-commerce sales, customer invoices and Accounting). Custom JK ERP/Clinical owns Doctor/Patient, Appointment, OPD/EMR, Care Plan, Clinical Billing workflow, ARM, Attendance and Payroll calculation. |
| Cloud posture | Hybrid-leaning-cloud | Managed cloud for applications/data, with local resilience for clinical/outlet continuity where internet dependence is unacceptable. |
| Integration model | API-first + domain events | No direct cross-domain database access; synchronous APIs for commands/queries, events for decoupled downstream reactions. |
| Identity | One JK ID | A single party identity can hold Customer, Patient, Member, Employee or Vendor roles without duplicate customer records. |
| Migration | Parallel run, no big bang | Rehearse in staging, shadow/parallel run, reconcile, preserve rollback and cut over outlet/module by module. |
| Delivery | Continuous UAT + gated releases | Two-week sprints, demos, targeted UAT, security/performance/DR evidence before major go-live. |

## 3.2 Layered system architecture

| Layer | Primary components | Responsibility |
| --- | --- | --- |
| Experience / Channel | Super Website; Super App; Staff Apps; Custom ERP/Clinical Console; Odoo Community POS/Admin | Customer, workforce, clinical and commercial operations interfaces. Website/App remain JK-owned experiences; Odoo processes commercial transactions behind controlled adapters/APIs. |
| Shared Foundation / Control Plane | JK ID/SSO; API Gateway; RBAC; Consent; Notification; CMS; Search; Payment; Loyalty; Audit | Central identity, policy enforcement, common communications and cross-platform governance. |
| Business Domains | Commercial/Financial ERP (Odoo); Clinical/Care; HR/ARM/Workforce; Membership/Fitness; Community/Education; Data/AI | Bounded contexts with explicit ownership. Odoo is authoritative for commercial/financial records; custom domains own differentiated operational workflows. |
| Data, Events & Intelligence | PostgreSQL; Redis; RabbitMQ; Object Storage/CDN; Warehouse; AI/ML services | Operational persistence, cache/session, asynchronous events, media, analytics and model workloads. |
| Integration | Payment/MFS; SMS/Email/WhatsApp; Health Connect/HealthKit; wearable APIs/BLE; Sinbad; biometric/lab devices | Adapters isolate external providers and Odoo integration contracts from custom domain logic, preserving replaceability and controlled coupling. |

•  Boundary rule: each domain owns its data; other domains consume APIs or events, never shared tables.

•  Evolution rule: Clinical and AI/Food Recognition are the first likely candidates for independent service extraction because of health-data isolation and inference workloads.

•  Data rule: events required for alerts, analytics and future prediction are captured from day one; historical data cannot be retrofitted later.

•  Migration rule: no production cutover without rehearsal, reconciliation, rollback and business-owner sign-off.

## 3.3 Domain ownership & ERP boundary

| Domain | System of record / ownership | Scope |
| --- | --- | --- |
| Identity & Shared Platform | Custom / JK Tech | JK ID, authentication, RBAC, consent, notification, audit, API gateway, integration contracts and identity mapping to Odoo customer/partner records. |
| Commercial & Financial ERP | Odoo Community + JK Tech integration boundary | Product, Inventory/Warehouse, Procurement, POS, outlet sales, online/e-commerce sales processing, customer invoices, payment/reconciliation and Accounting/ledger. |
| Clinical & Care Plan | Custom / JK Tech + Clinical SME | Doctor Profile, Patient, Appointment request/process, OPD, EMR, consent, Care Plan authoring, tasks, alerts and clinician workflow. |
| HR / ARM / Workforce | Custom / JK Tech | ARM, employee/workforce data, Attendance and Payroll calculation/approval workflow. Approved financial summaries post to Odoo Finance. |
| Digital Commerce Experience & Booking | Custom channels + Odoo transaction engine | Next.js Website/Super App own UX, discovery, cart/checkout orchestration and non-commercial bookings; Odoo processes product sales/orders, stock and financial transaction records. |
| Membership / Fitness / CRM | Custom / JK Tech | Membership lifecycle, classes, profile and CRM/Customer 360 read model over shared JK ID and cross-system references. |
| Community / Education / Franchise | Custom / JK Tech | Community feed, moderation console, LMS/video, franchise/distribution and field-operation workflows. |
| Data / BI / AI | Custom / JK Tech | Event capture, warehouse, dashboards, adherence analysis and future model-serving layer; consumes Odoo and custom-domain events/read models, not direct shared tables. |

ERP boundary. Odoo Community is a core commercial/financial application, not a generic shared database. It is the system of record for products/stock, POS and sales transactions, customer financial invoices, payments/reconciliation and the accounting ledger. The custom JK ERP/Clinical platform owns clinical and workforce context. A clinical invoice is created/approved in the custom Clinical workflow, then posted to Odoo for accounting/payment/ledger; approved payroll results follow the same rule. Website and Super App remain JK-owned experiences but route e-commerce transaction processing to Odoo through an adapter/API. No custom service writes directly to Odoo tables; integrations use supported APIs/contracts/events and carry idempotency/correlation identifiers.

## 3.4 Identity & data architecture

| Entity | Purpose | Primary consumers |
| --- | --- | --- |
| party (JK ID) | Identity root: name, contact, authentication identity and consent linkage | All channels and custom domains; mapped to Odoo partner/customer reference |
| party_role | Customer / Patient / Member / Employee / Vendor role linkage | CRM, Clinical, Membership, HR/ARM |
| odoo_product / lot / stock reference | Odoo-owned product, batch/lot, warehouse and stock movement identifiers exposed through adapter/read models | Website/App catalogue read model, fulfillment, traceability, reporting |
| appointment | Patient, doctor, request/status, schedule, location and service context | Custom ERP/Clinical, App/Website booking, notifications |
| care_plan / target / task | Plan versions, typed targets and daily/weekly tasks | Clinical authoring, App planner, alerts |
| device_reading | Time-series glucose, weight, BP, steps, sleep, source and timestamp | App, Alert Engine, Warehouse |
| clinical_bill | Clinical services, professional/service context, approval status and Odoo invoice reference | Custom Clinical workflow; Odoo financial posting/payment |
| attendance / payroll_run | Attendance inputs, payroll calculation, approval status and Odoo journal/payable reference | Custom HR/ARM/Payroll; Odoo Finance |
| commercial_order reference | Odoo sales/POS/e-commerce order ID, channel, customer mapping and fulfillment/payment status | Website/App read models, CRM, analytics, support |

•  Traceability: product_batch links origin → stock ledger movements → final order line, supporting FEFO and Farm/Outlet/Customer traceability.

•  Care Plan extensibility: targets use metric_code + value + unit rather than fixed columns, so new clinical metrics do not require repeated schema migrations.

•  CRM/Customer 360 is a read model over the shared JK ID and role relationships, not a second master customer table.

## 3.5 Integration, offline sync & real-time event architecture

| Area | Pattern | Control / behavior |
| --- | --- | --- |
| Offline POS | Odoo POS native/offline session capability + controlled synchronization | Use Odoo Community POS as the transaction engine. Validate target-version offline behavior, browser/device cache, reconnect and payment constraints during pilot; do not build a second custom POS ledger unless the gap analysis proves it necessary. |
| Stock conflict | Odoo authoritative stock moves + reconciliation | Odoo remains authoritative for stock/reservation/movement. Custom apps consume stock availability via APIs/read models and never overwrite stock tables. Reconnect conflicts and duplicate submissions use transaction IDs/idempotency plus reconciliation reports. |
| Cash/shift close | Odoo POS session/payment reconciliation | Outlet cash/session close and payment records reconcile in Odoo. Network recovery, duplicate-order prevention and stock/payment reconciliation are explicit pilot acceptance tests. |
| Wearables / CGM | Health Connect + HealthKit first | Direct vendor API or BLE where required; manual entry always remains available via the same backend endpoint. |
| Event backbone | RabbitMQ first | Single ingestion path can feed Alert Engine, notifications and Warehouse; Kafka only if proven event volume justifies it. |
| Notifications | FCM/APNs + WebSocket | Domain events trigger mobile push; WebSocket supports OPD queue and live manager dashboards. |
| Reliability | Idempotency + retry + trace IDs | Repeat-safe processing, correlation IDs and observable retry behavior for offline and vendor-failure scenarios. |
| Community feed | Hybrid consistency | Immediate consistency for a user's own write; ranked feed re-scored asynchronously. |

Clinical alert flow. Dangerous reading → Alert Engine rule → patient notification and clinician task in parallel → clinician acknowledgement SLA → escalation to on-call supervisor when unacknowledged. The platform provides reliable delivery and an audit trail; it is monitoring infrastructure, not an emergency-response replacement.

## 3.6 Security, privacy & resilience architecture

| Control area | Implementation |
| --- | --- |
| Authorization | RBAC scoped by Concern, Location and Function; enforced at gateway/service boundary, not only in UI. |
| Authentication | Mandatory 2FA for staff/admin; OTP-based consumer/patient login to reduce onboarding friction. |
| Encryption | TLS in transit, encryption at rest, plus field-level encryption for sensitive EMR/device/Care Plan fields. |
| Audit | Sensitive health-data access logged on reads as well as writes; correlation/trace IDs retained for investigations. |
| Consent | Explicit, revocable consent records govern device sharing, community use and analytics/AI processing. |
| Application security | Dependency scanning, SAST and OWASP controls in CI; independent VAPT before major go-lives and annually thereafter. |
| Backup / DR | Automated backups, restore tests and module-specific RTO/RPO; DR rehearsal before major public releases. |
| Local resilience | Secured VPN and optional local edge/cache at Dhaka flagship; other outlets use offline-first POS with background sync. |
| Observability | Structured logs, trace IDs, metrics, SLO dashboards, vulnerability backlog and monthly cloud/cost review. |

## 3.7 Technology platform & DevOps

| Layer | Choice | Reason |
| --- | --- | --- |
| Web | Next.js (React) + TypeScript | SSR/SEO, reusable component library, broad hiring pool. |
| Mobile | Flutter | Single Android/iOS codebase, offline store, BLE/device ecosystem. |
| Backend | Node.js / NestJS | Strong modular boundaries, TypeScript contracts and API-first service design. |
| AI / data services | Python / FastAPI | ML/data-science ecosystem and model-serving path. |
| ERP | Odoo Community (open-source baseline) | Commercial/financial core: Product, Inventory/Warehouse, Procurement, POS, outlet + online/e-commerce sales, customer invoicing, payment/reconciliation and Accounting. |
| Primary DB | Managed PostgreSQL | ACID for finance/clinical and JSONB for controlled semi-structured targets. |
| Cache/session | Redis | Session, rate limiting, cache and selected queue/state use cases. |
| Events | RabbitMQ → Kafka only if justified | Operationally simpler at current scale; future throughput path remains open. |
| Search | PostgreSQL FTS → OpenSearch when needed | Avoid search-cluster operational cost before catalogue/community volume requires it. |
| Object/media | S3-compatible object storage + CDN | Food/progress images and education media with compression/lifecycle policies. |
| Runtime | Managed Kubernetes | Dev/Staging/Prod parity, horizontal scaling and workload isolation. |
| CI/CD | GitHub Actions + Argo CD (or equivalent) | Traceable commit-to-deployment pipeline with gated production promotion. |

## 3.8 Data & AI architecture

| Pipeline step | Architecture | Governance / control |
| --- | --- | --- |
| 1. Capture | Food photo, user correction, device reading, adherence outcome | Write consent/data-lineage metadata with the event. |
| 2. Recognize | Third-party food-recognition API + locally curated Bangladeshi nutrition data | Buy phase accelerates launch while local data remains JK-owned. |
| 3. Human confirm | Confidence score + correction when below threshold | Manual correction is a first-class product path and safety control. |
| 4. Store & label | Consented events land in warehouse/training dataset | Corrections become labeled examples; preserve source and model/version lineage. |
| 5. Build decision | Local model POC after sufficient labeled data exists | Compare quality, latency and cost before shifting inference in-house. |

•  Indicative Phase-2 quality target: >=80% correct dish identification with an approximate ±20% macro/portion estimate target; always expose confidence and confirmation when uncertain.

•  Inference cost control: cache common/repeated meals and batch non-urgent recognition rather than paying synchronous vendor cost for every photo.

•  Warehouse prerequisites: event capture, stable metric_code conventions, consent tagging and data lineage are established before predictive models depend on them.

## 3.9 Key end-to-end system flows

| Flow | Path | Architecture intent |
| --- | --- | --- |
| Care Plan | Clinician Console → Clinical Service → PostgreSQL → domain event → App Care Plan API → patient | Clinical remains the authoring source of truth; the App consumes a stable API contract rather than reading clinical tables. |
| Meal / AI | Super App → Object Storage → recognition API/local nutrition → user confirmation → event → warehouse/adherence → clinician dashboard | Separate media, inference and analytics paths; corrections become labeled data with consent and lineage. |
| Online / e-commerce sale | Website/Super App → API Gateway / Odoo Adapter → Odoo Sales/e-commerce transaction → payment → Odoo stock/financial posting → domain events/read models | JK owns the customer experience; Odoo Community owns the commercial transaction, inventory impact and financial record. |
| Outlet / POS sale | Odoo POS → Odoo sales/inventory/accounting → integration events/read models → CRM/BI/support | One POS/commercial source of truth; custom systems consume results rather than duplicating sale or stock ledgers. |
| Clinical invoice | Custom ERP/Clinical → clinical services/bill approval → integration → Odoo customer invoice/payment/accounting reference | Custom Clinical owns medical/service context; Odoo owns the financial invoice, payment/reconciliation and ledger. |
| Payroll | Custom ERP Attendance/Payroll → payroll approval → integration → Odoo Finance journal/payable/ledger reference | Custom ERP owns attendance and payroll calculation; Odoo owns the final accounting impact. |
| Offline POS | Odoo POS offline/session mode → reconnect/sync → Odoo authoritative transaction/stock/payment reconciliation | Offline acceptance is validated against the selected Odoo Community version; idempotency and reconciliation protect recovery. |
| Authentication | Channel → JK ID/SSO → role/consent resolution → token → API Gateway → custom domain or Odoo adapter | Identity and authorization remain centralized while Odoo customer/employee references are mapped, not duplicated as a competing identity master. |

## 3.10 Deployment topology & non-functional baseline

| Area | Baseline design | Control / target |
| --- | --- | --- |
| Environment model | Separate Dev, Staging and Production with isolated secrets/configuration | Every deployment traceable to source control; production promotion is gated. |
| Cloud runtime | Managed Kubernetes + managed PostgreSQL + Redis + RabbitMQ + object storage/CDN | Scale progressively rather than provisioning Phase-5 capacity on day one. |
| Connectivity | Cloud-first with secured VPN/local resilience for flagship clinical operations | OPD/POS continuity during ISP outage; background synchronization on recovery. |
| Scale design | 11 outlets initially; 500-700 daily patients; 5,000 peak concurrent users; 50,000+ Year-1 registered users | Horizontal scaling and cache/CDN reduce origin pressure as usage grows. |
| Resilience | Automated backups, restore tests, defined RTO/RPO and DR rehearsal | Clinical/Finance receive stricter recovery targets than community/content workloads. |
| Observability | Structured logs, metrics, trace IDs, SLO dashboard, alerting | Monthly reliability, vulnerability and cost review with threshold alerts. |

## 3.11 Concise answers to key board questions

These concise answers summarize the controls already defined in the architecture, delivery, risk and operating-cost sections.

| Q | Question focus | Concise answer |
| --- | --- | --- |
| Q10 | Top project-failure risks | Three primary failure drivers to control are: (1) dirty Odoo/Excel/master data - profile early, migrate in stages, reconcile and verify stock before cut-over; (2) clinical workflow churn - embed the Clinical SME, prototype early and sign acceptance criteria before build; (3) capacity/scope pressure - phase hiring, use specialist bridge support when needed, and enforce Definition of Done, change control and quarterly gates. |
| Q14 | Community moderation at scale | Use a hybrid moderation model: technology auto-flags health-misinformation patterns, while humans make moderation decisions through a Moderation Console under an SLA. Moderation tooling and minimum moderation capacity are hard Community go-live gates; automation assists detection, but health-content decisions are not delegated to AI alone. |
| Q15 | Responsibility for dangerous alerts | A dangerous reading triggers the Alert Engine, which notifies the patient and creates the assigned clinician task in parallel. The clinician is accountable within a defined SLA; unacknowledged alerts escalate to the on-call supervisor. Reliability is protected with queued events, idempotent retry, delivery monitoring, trace IDs and an audit trail; the platform is monitoring infrastructure, not the emergency responder. |
| Q16 | Controlling media and AI run cost | Right-size compute with autoscaling limits; compress images, use CDN caching, adaptive-bitrate video and lifecycle/cold-storage rules; cache repeated/common meal recognition and batch non-urgent AI processing. Track storage/CDN/AI unit costs monthly with budget alerts, and move from Buy to Build only when model quality and economics justify it. |

# 4. 24-Month Delivery Roadmap

Scheduling model. The phases intentionally overlap. Dependencies are respected (identity/master data before integration testing; Clinical authoring before the App Care Plan loop), while independent teams work in parallel to reduce calendar time. UAT happens throughout the program rather than as a final-stage activity.

## 4.1 Months 1-12

| Month | Primary Focus | Major Deliverables | Acceptance / UAT Gate |
| --- | --- | --- | --- |
| M1 | Mobilize & discover | Steering cadence; architecture decision register; concern-by-concern discovery; access to Odoo/data; baseline NFRs; security/data classification | Approved scope v1; risk register; prioritized backlog |
| M2 | Foundation v1 | Cloud accounts; Dev/Staging/Prod; Git/CI/CD; API Gateway skeleton; JK ID model; master-data rules; Odoo Community module/version & gap analysis | Environment readiness review; identity design sign-off; Odoo baseline confirmed |
| M3 | Odoo commercial core starts | Odoo Community Finance/Inventory cleanup; Product/Warehouse/Procurement/POS/Sales/e-commerce configuration; customer/employee/patient migration tooling; integration contracts; MIS consolidation | Data-quality report; Odoo module gap report; migration rehearsal #1 |
| M4 | Odoo POS pilot + Custom ERP/Clinical start | Odoo POS/outlet-sales pilot; stock/lot/FEFO configuration; Website-to-Odoo commerce adapter design; Doctor Profile and Appointment workflow discovery; Website design system | Odoo POS alpha UAT; offline/reconnect tests; clinical workflow sign-off |
| M5 | Commercial + workforce workflows | Odoo POS sale/return/session/payment and online sales order flow; custom ERP ARM, Attendance and Payroll core; patient registration; Appointment/OPD queue; website catalogue/cart APIs | Outlet + online-sales UAT; workforce UAT; clinical desk UAT |
| M6 | Odoo Commercial Gate 1 | Shadow-mode POS pilot; inventory/payment/accounting reconciliation; online order end-to-end test; MIS v1; pilot training; custom ERP workforce baseline | Gate 1: Odoo POS/commercial pilot accepted; reconciliation passed; VAPT #1 / security review |
| M7 | Odoo rollout + Custom ERP/Clinical build | Roll Odoo POS/commercial flow to first outlet wave; EMR core; consent/audit; website frontend connected to Odoo product/stock/sales APIs; unified login/cart | Outlet-wave UAT; online-commerce regression; EMR test cases signed off |
| M8 | App workstream starts | Care Plan authoring; website commerce transaction processing through Odoo; Flutter foundation; notification framework; AI-food API procurement | Website beta; Odoo commerce integration review; mobile architecture review |
| M9 | Clinical pilot + App core | Clinical pilot; website full journey with Odoo sales processing; app login/profile; care-plan read APIs; membership model; clinical billing-to-Odoo posting prototype | Clinical pilot UAT; web/Odoo regression UAT |
| M10 | Clinical + Website v1 go-live | Patient/Doctor/Appointment/OPD/EMR + basic Care Plan live; Group Hub/UOL online commerce processed by Odoo; clinical invoice financial posting operational | Gate 2: production go-live; Odoo/Clinical reconciliation; VAPT #2 |
| M11 | Care loop implementation | App planner/tasks; manual food log; reminders; membership/fitness; CRM/Customer 360 read model | App feature UAT; care-team acceptance |
| M12 | AI + device + community foundation | Food recognition buy-phase; Health Connect/HealthKit foundation; community moderation console; analytics events | AI accuracy baseline; moderation go-live checklist |

## 4.2 Months 13-24

| Month | Primary Focus | Major Deliverables | Acceptance / UAT Gate |
| --- | --- | --- | --- |
| M13 | Super App beta | App care plan; nutrition log; membership; CRM; notifications; basic device sync; pilot cohort | Closed beta + clinician/patient UAT |
| M14 | Super App v1 go-live | Care Plan loop end-to-end; Food Log AI; basic wearable/CGM path; operational support model | Gate 3: App v1 accepted; VAPT #3 |
| M15 | Community/LMS beta | Community feed + moderation; LMS/course delivery; franchise/distribution workflows; staff-app prototypes | Moderation UAT; franchise process sign-off |
| M16 | Community live + Data platform | Community v1; education v1; central warehouse foundation; event ingestion; BI semantic model | Content-safety gate; data-quality checks |
| M17 | Franchise & staff operations | Franchise/distribution; corporate MOU; Health Tourism/Sinbad integration if API verified; delivery/sample/field staff apps | Integration UAT; field pilot |
| M18 | Phase 4 Gate | Community/Education/Franchise/staff apps release; operating procedures and training | Gate 4: business acceptance; operational handover |
| M19 | Data/BI scale | Warehouse pipelines; advanced role-based dashboards; finance/clinical/commerce KPI layer | BI reconciliation against source systems |
| M20 | Predictive analytics prototype | Adherence/drop-off model prototype; cohort features; alert-quality monitoring; dataset governance | Offline model evaluation; clinical SME review |
| M21 | In-house food model POC | Local dataset training loop; model-serving POC; buy-vs-build cost benchmark | Model quality/cost decision gate |
| M22 | Scale-out | Manager dashboard app; outlet scale support 15-20; performance tuning; autoscaling/budget optimization | Load/performance UAT; DR rehearsal |
| M23 | Hardening & transition | Security hardening; audit cleanup; upgrade rehearsal; ownership transfer from specialists to JK Tech | KT acceptance; runbook audit; resilience test |
| M24 | Program close / steady state | Stabilization; backlog triage; SLO dashboard; annual operating model; Year-3 roadmap | Gate 5: program closure; BAU ownership accepted |

# 5. First 90 Days - Week-by-Week Execution Plan

| Week | Focus | Deliverables | Done / Acceptance |
| --- | --- | --- | --- |
| W1 | Program mobilization | Confirm sponsors/owners, RAID log, stakeholder map, decision cadence, repo ownership, access request list | Kickoff minutes + accountable owner per concern |
| W2 | Current-state & data audit | Odoo modules, Excel sources, website, patient/clinical workflows, master-data duplicates, integration inventory | As-is inventory + migration risk report |
| W3 | Cloud / engineering baseline | Dev/Staging/Prod; network/IAM; secrets; repository; branch/release model; CI skeleton | Environment checklist |
| W4 | Platform skeleton | API Gateway; observability; logging/trace IDs; auth architecture; backup baseline; security standards | Architecture review #1 |
| W5 | JK ID / SSO | Party/role model; OTP/staff 2FA; token flow; consent linkage; first end-to-end login | Identity demo + security UAT |
| W6 | Master Data | Product/customer/employee schemas; mapping rules; data cleansing scripts; staged imports | Migration rehearsal #1 |
| W7 | Odoo Community stabilization | Finance/inventory gap analysis; product/warehouse/POS/sales/e-commerce module configuration; supported API/integration contract | Odoo remediation + configuration backlog approved |
| W8 | Odoo POS & sales core | POS sale/return/session/payment; product/stock availability; outlet sales and online sales-order API; reconnect/offline test plan | Odoo POS + online sales alpha demo |
| W9 | Offline, idempotency & reconciliation | Validate Odoo POS offline/reconnect behavior; duplicate transaction protection; stock/payment reconciliation; failure/retry rules for Website/App adapter | Network-failure + reconnect test |
| W10 | MIS & migration rehearsal | Sales/stock/accounting MIS; Odoo/Excel reconciliation; pilot outlet master data; custom ERP employee/patient mapping | MIS sign-off + migration rehearsal #2 |
| W11 | Pilot outlet + online UAT | Staff training; device/printer/payment tests; outlet POS + online order parallel-run script; support channel | Pilot-readiness checklist |
| W12 | Shadow-mode pilot & Gate 1 prep | Live Odoo POS/commercial shadow usage; defect burn-down; stock/payment/accounting reconciliation; management demo; next-quarter plan | Go/no-go for controlled Odoo commercial cut-over |

# 6. Workstreams, Parallelism & Critical Dependencies

| Workstream | Active Window | Scope | Critical Dependency |
| --- | --- | --- | --- |
| Foundation / Platform | M1-M24 | JK ID, API Gateway, CI/CD, observability, security, notification, integration contracts | Blocks integration testing for every product stream |
| Odoo Commercial / Financial ERP | M2-M8 build/rollout; then BAU/enhance | Odoo Community Product, Inventory/Warehouse, Procurement, POS, outlet sales, online/e-commerce sales processing, customer invoices, payment/reconciliation, Accounting and MIS | Master data + Odoo module/version validation + stock/payment/accounting reconciliation |
| Custom ERP / Clinical / Workforce | M4-M10 core; M11+ enhance | Doctor Profile, Patient, Appointment, OPD/EMR, Care Plan, clinical billing workflow, ARM, Attendance and Payroll calculation | Clinical SME + identity + Odoo finance-posting contracts + audit/security |
| Website | M4-M10 | Group hub and customer commerce UX, Health Revolution booking, unified login/cart; product/stock/sales processing through Odoo APIs/adapter | JK ID + Odoo product/stock/sales contracts + booking APIs |
| Super App / Care Plan | M8-M14 | Customer app, care plan loop, food log, membership, devices, notifications | Clinical authoring model must be stable |
| Community / Education | M12-M18 | Feed, moderation, LMS, content/video, expert presence | Moderation console and content policy are hard go-live gates |
| Franchise / Staff Apps | M14-M18 | Distribution, corporate/health tourism integrations, field staff apps | Verified partner APIs + stable inventory/identity |
| Data / BI / AI | M1 event capture; M16-M24 maturity | Warehouse, dashboards, adherence prediction, local food model evolution | Event/data lineage and consent capture must exist from day one |

# 7. Team Ramp & Responsibility Model

| Period | Approx. Team Size | Composition | Primary Delivery Load |
| --- | --- | --- | --- |
| M1-2 | 6.0 | Architect, 2 backend, DevOps, 0.5 QA, Odoo specialist, 0.5 UI/UX | Foundation + Odoo discovery |
| M3-6 | 8.5 | Architect, 3 backend, DevOps, QA, Frontend, Odoo specialist, 0.5 UI/UX | ERP/POS + early Clinical/Website |
| M7-10 | 13.5 | Architect, 4 backend, DevOps, 2 QA, 2 Frontend, 2 Mobile, Odoo specialist, 0.5 UI/UX | Peak Clinical/Website + App start |
| M11-14 | 14.0 | Architect, 4 backend, DevOps, 2 QA, 2 Frontend, 3 Mobile, in-house Odoo | Super App / Care Plan peak |
| M15-18 | 12.0 | Architect, 4 backend, DevOps, 2 QA, Frontend, 2 Mobile, in-house Odoo | Community/Franchise + Data foundation |
| M19-24 | 11.0 | Architect, 3 backend, DevOps, 2 QA, Frontend, 2 Mobile, in-house Odoo | Scale, BI/AI, hardening, KT |

Role consolidation. No separate Product Owner, Data/AI Engineer, ML/AI Specialist or Community Moderator headcount is included in this budget; those responsibilities are covered by the Tech Lead / Architect. Clinical/Domain SMEs are seconded from Health Revolution and therefore are not treated as incremental payroll. Their availability remains a hard delivery dependency for workflow and safety sign-off.

# 8. Cost Model

Costing follows the architecture and delivery model above. The baseline uses the recalculated role assumptions, 15% in-house loading, specialist Odoo/UIUX support, a progressive infrastructure ramp, and a 12% centrally controlled contingency. Product Owner, Data/AI, ML/AI and Community Moderation responsibilities are covered by the Tech Lead / Architect in this baseline.

## 8.1 Costing basis & numeric assumptions

Why numeric assumptions are required. The baseline document intentionally used relative cost weights instead of fixed currency values. For financial planning, this version converts that shape into a BDT baseline using role-rate assumptions. These rates are placeholders for budgeting and must be replaced by HR offers and signed supplier quotations before procurement.

## 8.2 Role-rate assumptions

| Role | Mode | Planning Rate (BDT/month) | Scope |
| --- | --- | --- | --- |
| Tech Lead / Architect | In-house | 200,000 | Architecture, security, vendor governance, product/backlog ownership, process mapping, acceptance criteria, Data/AI & ML oversight, community moderation governance, final go-live sign-off |
| Senior Backend Engineer | In-house | 100,000 | API Gateway, core platform, domain architecture |
| Mid Backend Engineer | In-house | 80,000 | Custom ERP/Clinical, ARM/Attendance/Payroll, Odoo integration adapters, membership and community services |
| Frontend Engineer | In-house | 80,000 | Next.js website/admin experiences |
| Flutter Mobile Engineer | In-house | 70,000 | Super App, offline sync, device integrations |
| QA / Test Engineer | In-house | 50,000 | Manual + automation + release/UAT coordination |
| DevOps / Platform Engineer | In-house | 100,000 | Cloud, Kubernetes, CI/CD, security baseline, observability |
| Odoo/ERP Engineer (after transition) | In-house | 70,000 | Odoo Community Product/Inventory/POS/Sales/e-commerce/Finance extension, supported integrations and maintenance |
| Odoo Specialist | Outsourced | 70,000 / FTE-month | Initial Odoo Community stabilization and configuration across Finance/Inventory/POS/Sales/e-commerce, integration support and knowledge transfer |
| UI/UX Designer | Contract | 80,000 / month | Design system, low-literacy UX, service flows |

## 8.3 Development and specialist cost by delivery block

| Period | In-house Payroll / mo (M BDT) | External / mo (M BDT) | Loaded Dev Cost / mo* (M BDT) | Period Total (M BDT) |
| --- | --- | --- | --- | --- |
| M1-2 | 0.505 | 0.110 | 0.691 | 1.382 |
| M3-6 | 0.690 | 0.110 | 0.904 | 3.614 |
| M7-10 | 1.040 | 0.110 | 1.306 | 5.224 |
| M11-14 | 1.180 | 0.000 | 1.357 | 5.428 |
| M15-18 | 1.030 | 0.000 | 1.185 | 4.738 |
| M19-24 | 0.950 | 0.000 | 1.093 | 6.555 |
| TOTAL |  |  |  | 26.941 |

*Loaded development cost. In-house payroll is loaded with 15% for employer overhead/benefits/recruitment friction; external specialist rates are treated as fully loaded. No separate Product Owner, Data/AI Engineer, ML/AI Specialist or Community Moderator FTE is budgeted; those responsibilities are included in the Tech Lead / Architect baseline. The separate recruitment/onboarding budget covers hiring campaigns, joining equipment gaps and exceptional onboarding costs.

| Cost Category | 24-Month Base (M BDT) | Planning Note |
| --- | --- | --- |
| Loaded engineering + outsourced specialists | 26.9 | Core technical delivery team plus Odoo/UIUX specialist support; consolidated roles absorbed by Tech Lead |
| Cloud / platform infrastructure | 10.0 | Compute, managed DB, Redis/queue, storage/CDN, backup/DR; grows by phase |
| AI / Nutrition API consumption | 1.8 | Buy-phase food recognition/nutrition baseline; controlled by caching/batching |
| Communication / Maps / Monitoring / SaaS | 2.4 | SMS/email/WhatsApp baseline, maps, APM/logging, low-volume tools |
| Independent VAPT / security testing | 1.8 | Three major pre-go-live security assessments at ~0.6M each |
| Engineering/test equipment & field hardware | 2.5 | Developer/test devices, mobile devices, POS/peripheral lab and pilot equipment |
| Data migration, training & change management | 2.0 | Rehearsals, outlet/clinic training, cut-over support and reconciliation |
| Recruitment & onboarding reserve | 1.0 | Hiring campaigns, screening, joining/onboarding costs |
| Subtotal before contingency | 48.4 | Approved delivery baseline |
| Contingency reserve (12%) | 5.8 | Only released against approved risk/change |
| TOTAL PROGRAM ENVELOPE | 54.3 | ~BDT 5.43 crore over 24 months |

## 8.4 Infrastructure ramp assumption

| Period | Monthly Infra (M BDT) | Period Total (M BDT) | What drives cost |
| --- | --- | --- | --- |
| M1-3 | 0.12 | 0.36 | Foundation/dev/test + small production footprint |
| M4-6 | 0.20 | 0.60 | Odoo POS/commercial pilot + early Custom ERP/Clinical/Website |
| M7-12 | 0.30 | 1.80 | Odoo commercial production + Website/Clinical + App beta/media |
| M13-18 | 0.50 | 3.00 | Super App + food photos + Community/LMS + warehouse |
| M19-24 | 0.70 | 4.20 | Higher usage, BI/AI workloads, 15-20 outlet scale support |
| TOTAL |  | 9.96 | Rounded to BDT 10.0M in the program budget |

# 9. Quarterly Budget Release & Delivery Gates

| Budget Window | Base Release (M BDT) | Delivery Focus | Release / Acceptance Gate |
| --- | --- | --- | --- |
| Q1 - M1-3 | 4.79 | Foundation + identity/master data + Odoo Community baseline start | Architecture baseline, environments live, identity path demonstrated |
| Q2 - M4-6 | 5.06 | Odoo POS/commercial pilot + Custom ERP/Clinical/Website start | Odoo POS/outlet + online-sales pilot accepted; migration/reconciliation passed; VAPT #1 |
| Q3 - M7-9 | 6.06 | Odoo commercial rollout + Custom ERP/Clinical/Website build + App foundation | Clinical pilot ready; website/Odoo beta flow; App architecture accepted |
| Q4 - M10-12 | 7.06 | Clinical + Website go-live with Odoo commerce processing; App/Care loop build | Production gate + VAPT #2; Odoo/Clinical reconciliation; web/clinical BAU stable |
| Q5 - M13-15 | 6.88 | Super App go-live + Community/LMS beta | App v1 accepted + VAPT #3; closed-loop care functioning |
| Q6 - M16-18 | 6.33 | Community/Education/Franchise + warehouse | Phase-4 business acceptance; operational training complete |
| Q7 - M19-21 | 6.11 | BI/AI maturity + local model POC | Data reconciliation; model quality/cost decision |
| Q8 - M22-24 | 6.15 | Scale, DR, hardening, handover | Performance/DR/KT accepted; BAU ownership signed |
| Program contingency | 5.81 | Central reserve; not pre-allocated to quarters | Release only through Steering Committee change/risk approval |

Budget-control rule. Quarterly funds should be approved against the next delivery gate; monthly burn is reviewed by the Tech Lead and Finance. A forecast variance above 5% requires a written recovery plan; above 10% requires Steering Committee scope/time/budget approval.

# 10. Quality, UAT, Security & Release Strategy

| Cadence / Gate | Required Activities | Exit Condition |
| --- | --- | --- |
| Every sprint | Unit/integration tests, API contract checks, targeted business UAT, demo, security/dependency scan | Defects triaged before next sprint planning |
| Every month | Regression pack, cloud-cost review, vulnerability backlog, data reconciliation checks | Monthly delivery + burn report |
| Before outlet/clinic rollout | Migration rehearsal, staff training, parallel run, rollback plan, support roster | Business owner cut-over approval |
| Before major public go-live | Performance/load test, VAPT, DR/backup restore check, observability/SLOs, privacy/consent verification | Formal go/no-go chaired by Tech Lead + Business Owner |
| Post go-live 2-4 weeks | Hypercare, incident review, adoption metrics, backlog stabilization | Exit hypercare only when SLO/defect thresholds are stable |

# 11. Budget & Timeline Risks with Controls

| Risk | Exposure | Impact | Control |
| --- | --- | --- | --- |
| Hiring delay | High | Pushes critical path because JK Tech starts with no bench | Start Phase-2/3 hiring during Phase 0-1; keep approved specialist bridge contracts |
| Dirty Odoo/Excel data | High | Rework, reconciliation failure, rollout delay | Profile data in M1-2; stage migration; physical stock count before outlet cut-over |
| Clinical workflow churn | High | EMR/Care Plan rework | Embed clinical SME; prototype workflows early; sign acceptance criteria before build |
| Odoo over-customization | Medium/High | Upgrade/maintenance lock-in or recreating differentiated clinical/HR logic inside Odoo. | Keep Odoo focused on commercial/financial core; keep Clinical/ARM/Attendance/Payroll workflows in custom ERP; use supported APIs/adapters and regression tests for upgrades. |
| Cloud/media/AI usage spike | Medium | Run-cost exceeds envelope | Compression/lifecycle, caching/batching, quotas, monthly unit-cost dashboard |
| Vendor/API availability | Medium | Blocks Sinbad, wearable or AI features | Adapter interfaces; manual fallback; defer integrations that are not verified |
| Scope expansion | High | Budget and timeline drift | Definition of Done + change control; contingency is not a scope-slush fund |
| Security/compliance defect | High | Go-live delay and business risk | Security by design, field encryption, read-audit for health data, independent VAPT gates |

# 12. Limited-Budget / Half-Year-1-Budget Fallback

•  Defer Community Platform and Education/LMS before cutting the shared foundation, Odoo commercial core, or Custom ERP/Clinical.

•  Delay deep Wearable/CGM integration; keep manual entry and basic Health Connect/HealthKit capability where affordable.

•  Keep Food Recognition in buy-mode longer and delay the in-house model build; this preserves user value while avoiding early model investment.

•  Defer Franchise Management and Health Tourism/Sinbad integration until the core operating system is stable.

•  Do not cut JK ID/SSO, API Gateway, Master Data, core security (2FA/encryption/audit), Odoo commercial/financial core, or Custom ERP/Clinical foundation.

# 13. Program Governance & Reporting

| Cadence | Meeting / Control | Participants | Output |
| --- | --- | --- | --- |
| Daily | Engineering stand-up per workstream | Engineering leads | Blockers, defects, environment issues |
| Weekly | Architecture/vendor/risk review | Tech Lead + DevOps + module leads | RAID, ADRs, dependency plan, burn vs plan |
| Bi-weekly | Sprint review + UAT + planning | Business owners + engineering | Accepted increments and next sprint commitment |
| Monthly | Steering committee | GMO/CEO/CFO/Tech Lead | Budget, timeline, scope changes, risk decisions |
| Quarterly | Phase gate / budget release | Steering committee | Acceptance gate, next-quarter budget, hiring/vendor decisions |

# 14. Architect Recommendation

Adopt the architecture-led 24-month roadmap with quarterly funding gates and a BDT 54.3M planning ceiling, while treating BDT 48.4M as the delivery baseline and BDT 5.8M as controlled contingency. Preserve the synchronized technical model: one JK ID, Odoo Community as the commercial/financial system of record, a custom JK ERP/Clinical platform for Doctor/Patient/Appointment/EMR/Care Plan/Clinical Billing/ARM/Attendance/Payroll workflow, API/event integration between them, security/consent controls by design and gated releases. Stabilize master data and Odoo commercial operations, establish Custom ERP/Clinical, then scale App, Community and AI capabilities on top of trusted operational data. The costing assumptions remain unchanged pending the M1-M2 Odoo module/gap validation.

•  Approve Phase 0 and Q1 budget immediately only after named business owners and data-access owners are confirmed.

•  Validate all remaining role rates with HR and convert Odoo/UIUX placeholders into signed quotations before Q2 approval; validate any Odoo hosting/add-on/support and AI/API vendor consumption separately as operating/vendor costs.

•  Lock Odoo Community as the baseline and validate the exact supported version/modules, hosting model, POS offline/reconnect behavior, e-commerce/Sales APIs, backup/DR approach and any paid add-on/support requirements before commercial production scaling.

•  Use business acceptance and measurable technical gates (reconciliation, VAPT, performance, DR, UAT) as the condition for go-live and next-quarter budget release.

•  Review the cost model every quarter using actual salary, cloud unit cost, AI cost per food-log, SMS cost per active patient and storage/CDN cost per active user.

# Appendix A - Budget Formula & Reforecast Method

| Cost Driver | Formula | Control |
| --- | --- | --- |
| People cost | Sum(role count x monthly rate x active months) + 15% in-house loading | Reforecast on hiring date/rate changes; no separate PO/Data-AI/ML/moderator FTE in baseline |
| Cloud cost | Compute + DB + cache/queue + object storage + CDN + backup/DR | Track actual monthly unit cost; forecast from active users/content volume |
| AI cost | Recognition API calls x unit price + nutrition data + model serving compute | Track cost per confirmed food-log and cache hit rate |
| Communication | SMS/WhatsApp/email message volume x unit rate | Track messages per active customer/patient |
| Contingency | 12% of approved baseline | Not part of team discretionary spend; requires change/risk approval |

Final validation checklist. Before approval, Finance/HR should validate salary bands; Procurement should obtain Odoo Community implementation/hosting/add-on/support, AI/SMS/cloud/VAPT quotations; Business Owners should confirm scope and migration volumes; the Odoo pilot must validate POS offline/reconnect, outlet + online sales, inventory, payment/reconciliation and accounting flows; Legal/Compliance should confirm health-data residency and consent requirements. Material variances roll into the next quarterly budget gate.